| Risk Mitigation, Monitoring and Management (RMMM) Plan Project: Campus View — Smart Campus Event Information and Navigation System SRM Institute of Science and Technology, Kattankulathur ¦ Final Year Project 2025–2026 |  |
| --- | --- |
| Project Title | Campus View — Smart Campus Event Information and Navigation System |
| Team Members | HEET JAIN (RA2311003012210) ¦ VISHVA SHAH (RA2311003012211) ¦ HEMANG DUBEY (RA2311003012208) |
| Tech Stack | Node.js + Express + SQLite + React 18 + Tailwind CSS + Leaflet + OSRM |
| Document Date | 17 April 2026 |

# Step 1 & 2: Risk Table & Sorting

The following table lists all identified project risks sorted in descending order by probability of occurrence. Probability and Impact are assessed by the development team at the start of each sprint.

| ID | Risk Description | Cat. | Prob. | Imp. | RMMM Strategy Summary |
| --- | --- | --- | --- | --- | --- |
| RIS-01 | GPS permission denied / unavailable | TE | 70% | 2 | Graceful error message; straight-line fallback route drawn automatically. |
| RIS-02 | OSRM public API downtime or timeout | DE | 60% | 2 | Timeout after 5 s; fallback to straight-line; user notified via amber banner. |
| RIS-03 | JWT secret hardcoded in source code | SE | 55% | 1 | Move to .env; add .env to .gitignore; enforce before any deployment. |
| RIS-04 | Database ID corruption from re-seeding | DE | 50% | 2 | seed.js skips if data exists; reset.js clears + resets sqlite_sequence IDs. |
| RIS-05 | SQLite not suitable for concurrent load | TE | 45% | 3 | Acceptable at campus scale; document upgrade path to PostgreSQL if needed. |
| RIS-06 | Event date filter returns empty results | TE | 40% | 2 | Remove server-side date restriction; return all events; client filters. |
| RIS-07 | Schedule delay / sprint milestone missed | PD | 40% | 2 | Weekly sprints; MVP-first; buffer time per sprint; de-scope polish features. |
| RIS-08 | Map tiles unavailable (OpenStreetMap) | DE | 30% | 3 | Fallback tile layer URL; local tile cache for demo environment. |
| RIS-09 | GPS inaccuracy on desktop browsers | TE | 25% | 3 | Warn user if coords.accuracy > 50 m; test on mobile as primary device. |
| RIS-10 | Broken event image URLs in admin form | TE | 20% | 4 | onError handler hides broken preview; no crash; event saves without image. |

Category Codes — TE: Technology  |  DE: Dev Environment  |  SE: Security  |  PD: Process Definition

Impact Levels — 1: Catastrophic  |  2: Critical  |  3: Marginal  |  4: Negligible

Probability Colour Legend

| ≥ 65% — High Risk | 45–64% — Medium-High | 25–44% — Medium | < 25% — Low Risk |
| --- | --- | --- | --- |

Step 3: Risk Information Sheets (RIS)

## Risk Information Sheet: RIS-01 — GPS Permission Denied / Unavailable

| Probability: 70% | Impact: 2 |  | Category: TE | Assigned To: Frontend Developer | Date: 19/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | Student denies location permission or is on a device/browser without GPS. Navigation feature cannot show the user's position or generate a walking route. |  |  |  |
| Refinement & Context |  | 1. Mobile user denies permission when prompted. 2. Desktop browser has poor or no GPS support. 3. GPS signal unavailable indoors. |  |  |  |
| Mitigation & Monitoring |  | Show clear error message explaining how to enable location. Draw straight-line fallback route from venue marker to inform the user of direction. Test on mobile Chrome and Firefox. |  |  |  |
| Contingency Plan |  | Display static venue marker only with building address. Add manual 'Enter my location' pin-drop as future enhancement. |  |  |  |
| Trigger |  | GeolocationPositionError code === 1 (PERMISSION_DENIED) or code === 2 (POSITION_UNAVAILABLE). |  |  |  |

## Risk Information Sheet: RIS-02 — OSRM Public API Downtime or Timeout

| Probability: 60% | Impact: 2 |  | Category: DE | Assigned To: Frontend Developer | Date: 19/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | The OSRM public routing server (router.project-osrm.org) is unavailable or returns a timeout. No walking route can be generated for the student. |  |  |  |
| Refinement & Context |  | 1. OSRM is a free public demo server with no uptime SLA. 2. High traffic on public server causes slow responses. 3. Network latency on campus Wi-Fi. |  |  |  |
| Mitigation & Monitoring |  | Implement 5-second fetch timeout in fetchWalkingRoute(). On failure, call straightLineRoute() fallback. Show amber warning banner: 'Showing straight line — walking route unavailable.' |  |  |  |
| Contingency Plan |  | Cache the last successful route per event in sessionStorage. Consider self-hosting OSRM or switching to GraphHopper API for production. |  |  |  |
| Trigger |  | fetch() to OSRM throws network error or response.status !== 200 within 5 seconds. |  |  |  |

## Risk Information Sheet: RIS-03 — JWT Secret Hardcoded in Source Code

| Probability: 55% | Impact: 1 |  | Category: SE | Assigned To: Backend Developer | Date: 20/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | The JWT_SECRET is currently set as a string literal in auth.js. If the repository is made public or shared, tokens can be forged and any user account can be compromised. |  |  |  |
| Refinement & Context |  | 1. Current value: 'campus-view-srm-secret-change-in-production'. 2. GitHub exposure risk if accidentally pushed to public repo. 3. Secret rotation not possible without code change. |  |  |  |
| Mitigation & Monitoring |  | Move JWT_SECRET to server/.env file. Load via process.env.JWT_SECRET in auth.js. Add server/.env to .gitignore immediately. Add a pre-commit hook warning if .env is staged. |  |  |  |
| Contingency Plan |  | Rotate the secret immediately if exposure is detected. Invalidate all existing tokens by changing the secret value — all users will need to log in again. |  |  |  |
| Trigger |  | Repository made public; .env accidentally committed; security audit flags hardcoded secret. |  |  |  |

## Risk Information Sheet: RIS-04 — Database ID Corruption from Re-Seeding

| Probability: 50% | Impact: 2 |  | Category: DE | Assigned To: Backend Developer | Date: 20/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | Running node seed.js multiple times without resetting sqlite_sequence causes buildings and events to have non-sequential IDs. Foreign key references in events (building_id, floor_id) point to non-existent rows, causing empty API responses. |  |  |  |
| Refinement & Context |  | 1. SQLite AUTOINCREMENT does not reset on DELETE without clearing sqlite_sequence. 2. Re-seeding creates buildings with id=226 while events reference id=1. 3. JOIN queries return empty arrays silently. |  |  |  |
| Mitigation & Monitoring |  | seed.js checks if buildings > 0 AND events > 0 and skips if true. reset.js clears sqlite_sequence entries for buildings, floors, rooms, events before re-seeding. Verify IDs after seed with assertion check. |  |  |  |
| Contingency Plan |  | Add assertion: if(firstBuilding.id !== 1) throw error. Provide clear user instructions: always run node reset.js before node seed.js to force fresh IDs. |  |  |  |
| Trigger |  | GET /api/events returns [] despite events in DB; JOIN query on mismatched IDs. |  |  |  |

## Risk Information Sheet: RIS-05 — SQLite Not Suitable for Concurrent Load

| Probability: 45% | Impact: 3 |  | Category: TE | Assigned To: Backend Developer | Date: 21/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | SQLite uses file-level locking. Under concurrent write requests (multiple admins or automated tests), write operations may fail with SQLITE_BUSY errors. |  |  |  |
| Refinement & Context |  | 1. better-sqlite3 is synchronous and single-threaded. 2. Single-server campus deployment unlikely to exceed safe concurrency. 3. Read-heavy workload (students browsing events) is safe. |  |  |  |
| Mitigation & Monitoring |  | Enable WAL mode: db.pragma('journal_mode = WAL'). This allows concurrent reads with sequential writes. Document PostgreSQL upgrade path if user base grows beyond campus scale. |  |  |  |

## Risk Information Sheet: RIS-06 — Event Date Filter Returns Empty Results

| Probability: 40% | Impact: 2 |  | Category: TE | Assigned To: Backend Developer | Date: 21/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | Server-side date filtering using date('now', 'localtime') in SQLite returns no events when the server clock differs from the seed dates or when run on a different day than when seeds were created. |  |  |  |
| Refinement & Context |  | 1. SQLite date('now', 'localtime') is sensitive to system timezone. 2. Seeds generate dates using Node.js new Date() which may differ from SQLite local time. 3. Windows vs Linux timezone handling differences. |  |  |  |
| Mitigation & Monitoring |  | Remove server-side date restriction from GET /api/events. Return all events ordered by date. Let client-side filter handle date display. Only filter when ?date= query param is explicitly provided. |  |  |  |
| Contingency Plan |  | If server-side filtering is needed, pass the Node.js-generated date string as a parameter rather than using SQLite date functions. |  |  |  |
| Trigger |  | GET /api/events returns [] array on API test; all 14 seeded events in DB but none returned. |  |  |  |

## Risk Information Sheet: RIS-07 — Schedule Delay / Sprint Milestone Missed

| Probability: 40% | Impact: 2 |  | Category: PD | Assigned To: Scrum Master | Date: 21/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | Technical blockers (e.g. map integration, OSRM routing, GPS permission) or resource constraints cause sprint goals to slip beyond the planned delivery date. |  |  |  |
| Refinement & Context |  | 1. GPS navigation was significantly more complex than estimated. 2. Database ID corruption bug consumed 2 days of Sprint 1. 3. Team members balancing multiple academic commitments. |  |  |  |
| Mitigation & Monitoring |  | Weekly sprint retrospectives to identify blockers early. Prioritize MVP features: auth, event list, map, navigation. Mark polish features (bookmarks, splash, image banners) as Should Have and defer if needed. |  |  |  |
| Contingency Plan |  | De-scope Should Have user stories (US8, US10, US11) from current sprint. Reallocate to Sprint 4. Focus Sprint 3 on GPS navigation (US7) as the highest-value feature. |  |  |  |
| Trigger |  | Sprint milestone missed by > 3 days; critical path task blocked for > 2 days. |  |  |  |

## Risk Information Sheet: RIS-08 — OpenStreetMap Tiles Unavailable

| Probability: 30% | Impact: 3 |  | Category: DE | Assigned To: Frontend Developer | Date: 21/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | OpenStreetMap tile servers are temporarily unavailable or rate-limited. The campus map renders as an empty grey box. Building markers still render but no background map context is shown. |  |  |  |
| Refinement & Context |  | 1. OSM tile servers have occasional maintenance windows. 2. Heavy usage from multiple concurrent users may trigger rate limiting. 3. Campus network firewall may block tile server domains. |  |  |  |
| Mitigation & Monitoring |  | Configure a secondary TileLayer URL as fallback (e.g. CartoDB Positron: cartodb-basemaps.global.ssl.fastly.net). React Leaflet supports switching TileLayer on error event. |  |  |  |
| Contingency Plan |  | For demo environments, use a local tile cache or a tile proxy. Show a message: 'Map tiles unavailable — building markers still accurate.' |  |  |  |
| Trigger |  | TileLayer onError event fires; map renders as empty grey area. |  |  |  |

## Risk Information Sheet: RIS-09 — GPS Inaccuracy on Desktop Browsers

| Probability: 25% | Impact: 3 |  | Category: TE | Assigned To: Frontend Developer | Date: 21/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | Desktop browsers use IP-based geolocation which can place the user's blue dot hundreds of meters from their actual location. The walking route appears incorrect and unhelpful. |  |  |  |
| Refinement & Context |  | 1. Desktop geolocation uses Wi-Fi triangulation or IP lookup, not GPS satellite. 2. Accuracy values > 100 m are common on laptops. 3. Student may think the app is broken when dot is far from actual position. |  |  |  |
| Mitigation & Monitoring |  | Read coords.accuracy from the Geolocation API. If accuracy > 50 m, show warning banner: 'Low GPS accuracy detected. For best results, use on a mobile device.' This sets correct expectations. |  |  |  |
| Contingency Plan |  | Future: add manual pin-drop so user can place their marker at actual location. For demos: use a mobile phone on the same Wi-Fi to show accurate GPS. |  |  |  |
| Trigger |  | position.coords.accuracy > 50 returned from getCurrentPosition(). |  |  |  |

## Risk Information Sheet: RIS-10 — Broken Event Image URLs in Admin Form

| Probability: 20% | Impact: 4 |  | Category: TE | Assigned To: Frontend Developer | Date: 21/04/2026 |
| --- | --- | --- | --- | --- | --- |
| Description |  | Admin pastes an image URL that is valid at time of entry but later expires or becomes unavailable. Event cards show a broken image icon, degrading the student-facing UI. |  |  |  |
| Refinement & Context |  | 1. External image hosting services (Imgur, direct links) frequently expire. 2. No URL validation is performed beyond checking if it starts with 'http'. 3. Broken images appear as missing icon on event cards. |  |  |  |
| Mitigation & Monitoring |  | Add onError handler on all event card and detail banner <img> elements. On error, hide the image entirely so card layout is unaffected. Admin preview also handles broken URLs via onError. |  |  |  |

Step 4: Risk Monitoring Plan

The following monitoring activities are performed throughout the project lifecycle to detect risk triggers early and initiate mitigation actions before they impact sprint delivery.

| Risk ID | Monitoring Activity | Frequency | Responsible | Tool / Method |
| --- | --- | --- | --- | --- |
| RIS-01 | Test GPS on mobile Chrome and Firefox; check GeolocationPositionError codes | Each sprint | Frontend Dev | Manual testing on mobile devices |
| RIS-02 | Monitor OSRM API response times; test fallback route rendering | Weekly | Frontend Dev | Browser DevTools + console logs |
| RIS-03 | Audit server/.env existence; verify .gitignore includes .env | Before each commit | Backend Dev | Git status check + pre-commit hook |
| RIS-04 | Run node -e 'SELECT COUNT(*)' after seed; verify building id === 1 | After every seed run | Backend Dev | Terminal verification script |
| RIS-05 | Monitor server logs for SQLITE_BUSY errors under concurrent requests | Weekly | Backend Dev | Server console logs |
| RIS-06 | Test GET /api/events in browser; verify 14 events returned | After each server restart | Backend Dev | Browser + Postman |
| RIS-07 | Sprint retrospective; check task completion vs sprint goal | End of each sprint | Scrum Master | MS Planner board review |
| RIS-08 | Load campus map; verify tiles render; test secondary tile layer | Weekly | Frontend Dev | Browser visual check |
| RIS-09 | Check coords.accuracy on desktop browser; verify warning banner | Each sprint | Frontend Dev | Browser console + DevTools |
| RIS-10 | Click all event cards with images; verify no broken image icons | End of each sprint | Frontend Dev | Visual UI review |

Step 5: Overall Risk Summary

| Total Risks Identified | High Risk (≥ 65%) | Medium-High (45–64%) | Medium (25–44%) | Low Risk (< 25%) | Catastrophic Impact (Imp=1) |
| --- | --- | --- | --- | --- | --- |
| 10 | 1 (RIS-01) | 2 (RIS-02, RIS-03) | 5 (RIS-04 to RIS-08) | 2 (RIS-09, RIS-10) | 1 (RIS-03) |